## Senior design Ganntt
At Risk | Task Name | Start Date | End Date | Assigned To | Duration | % Complete | Predecessors | Comments
- | Watch how-to video on this template (4:16)
- | Click to learn how to use this template
| Build Responsibilities Setup Plan | 2016-01-25 | 2016-01-29 |  | 5d | 25%
| Team Kickoff Meeting | 2016-01-25 | 2016-01-27 | all | 3d | 50%
TRUE | finalize project timeline | 2016-01-27 | 2016-01-29 | Keith Runyon | 3d | 0%
| ensure ganntt timeline will not run out | 2016-01-27 | 2016-01-29 | Lucas Gintner | 3d | 0%
| Literature Review | 2016-09-22 | 2016-09-26 |  | 3d | 17%
| collect journal articles that are relevant | 2016-09-22 | 2016-09-22 | lee | 8h | 50%
| What problems have other researchers hit when modeling slot die caters with fea | 2016-09-23 | 2016-09-23 | zach peek | 4h | 0% | 10
| determine governing equations that most researchers use to model slot coating | 2016-09-23 | 2016-09-26 |  | 1.5d |  | 11, 7
| determine how 2 model anisotropic particales in non-newtonian fluid (mathmatically) | 2016-09-26 | 2016-09-26 |  | 0 |  | 12
| Programming Non-Newtonian Fluid Model | 2016-09-27 | 2016-09-30 |  | 4d
| determine which tutorials in SU and OpenFOAM are the most similar | 2016-09-27 | 2016-09-28 |  | 2d |  | 13
| complete similar tutorials | 2016-09-27 | 2016-09-28 |  | 2d
| build instructions on how to modify tutorial to fit our case | 2016-09-28 | 2016-09-30 |  | 3d
| identify problems with tutorial vs our case | 2016-09-29 | 2016-09-29 |  | 1d |  | 18
| Sample milestone | 2016-09-29 | 2016-09-29 |  | 0 |  | 20
| Programming Custom "System 1" Geometry into simple newtoanian Fluid Model | 2016-09-28 | 2016-09-30 |  | 3d